Table of Contents

# Sungas ERPNext — CONSOLIDATED ROADMAP (FULL SCOPE)

Last updated: June 2026 Status: Complete catalogue across all phases. Supersedes prior v1 roadmap that focused only on Wave C/D. This document is the master backlog.

## Legend

| Symbol | Meaning |
| --- | --- |
| ✅ | Live in production (tested) |
| 🚧 | In progress / partially shipped |
| ⏸ | Deferred / blocked on external input |
| 🔴 | P0 — blocks core ops or finance close |
| 🟠 | P1 — material improvement, next 1-2 sprints |
| 🟡 | P2 — important but not blocking |
| 🟢 | P3 — nice-to-have / future |
| 📦 | Backlog — scope captured, not scheduled |

## 1. Phase Index

| Phase | Title | Status | Items |
| --- | --- | --- | --- |
| Phase 1-4 | Foundation, masters, CoA, Customer migration | ✅ DONE | — |
| Phase 5 | POS Awesome — Pricing tier engine + cart UI | ✅ DONE | — |
| Phase 5.5 | POS Profile cloning, role profiles, cashier rollout, thermal receipt | ✅ DONE | — |
| Phase 5.7 | POS Awesome Hardening + variance accounts (4 new GLs) | ✅ DONE | — |
| Wave A-C | Sungas Close Policy + variance enforcement + UX + lockdown | ✅ DONE | — |
| Phase 6 | HRMS + Nigeria Payroll Cutover | 🚧 95 % DONE | 3 remaining items |
| Wave D | Sequential workflow + escalations + Ops routing | 🔴 NEXT | 9 items |
| Wave E | Path C Fraud Protocol | 🟠 PLANNED | 4 items |
| Phase 5.8 | POS Backup profiles per region | 🟡 PLANNED | 1 item (6 profiles) |
| Phase 5.9 | Manual Sales Book doctype | 🟡 PLANNED | 1 item |
| Phase 7 | Helpdesk (SLA, ticket flows, email) | 🟢 PLANNED | scope only |
| Phase 8 | CRM (pipeline + weekly dashboard) | 🟢 PLANNED | scope only |
| Phase A v1.1 | Engagement App expansion | 🟠 PLANNED | 9 items |
| Phase 9 | Period Close + UAT + opening balances | 🟢 PLANNED | 3 items |
| Phase 10 | Budgeting Module | 🟢 PLANNED | 1 item |
| Engineering | Equipment/Services onboarding + Manufacturing hygiene | 🟢 BACKLOG | 3 items |
| Bank Statement App | Already-built doctypes — needs deployment + UAT | 🟡 BACKLOG | UAT |
| Stakeholder SLA + KPI | Cross-cutting reporting layer | 🟠 PLANNED | 4 items |

## 2. ✅ DONE (full inventory)

### Foundation

- ✅ Fresh ERPNext v15 install on Frappe Cloud (sungasmis.v.frappe.cloud)

- ✅ Cleaned Customer + Chart of Accounts data migration

- ✅ Company, Cost Centers (21 outlet CCs), HRMS Branches, Sungas Region accounting dimensions

- ✅ sungasng/HR-Enhancements v13 → v15 port (commit c802054)

- ✅ sungasng/Sungas v13 → v15 port (commit 7a95d5a)

### Phase 5 — POS Awesome Core

- ✅ LPG Outlet Price Tier engine (Item × Customer Group × Territory × Qty)

- ✅ LPG Price Change Request (PCR) workflow: Draft → Head of Sales → Head of Finance → Approved → tier upsert

- ✅ 64-row price matrix seeded (seed_all_lpg_tier_rates.py)

- ✅ Strict tier mode (no tier → no sale)

- ✅ Cash-overage rounding with round-off account wiring

- ✅ Barcode receipt + Code 128 encoding INVOICE|QTY

- ✅ Mobile + search UI polish

### Phase 5.5 — POS Rollout

- ✅ 22 POS Profiles cloned per-outlet (Cost Centers, Cash/Transfer/POS-Incoming accounts, HRMS Branches)

- ✅ POS - Bulk Sales Benin disabled (wholesale via Sales Invoice)

- ✅ 4 LPG Role Profiles: POS User / Plant Manager / Head of Sales / Head of Finance

- ✅ 18 Plant Managers + 41 cashiers assigned profiles

- ✅ 2 missing cashiers provisioned (Emmanuel Nnorom, Nimota Sulaimon)

- ✅ POS Awesome switched to POS Invoice mode

- ✅ Custom DocPerm for LPG POS User (POS Invoice / Opening / Closing Shift)

- ✅ Sungas Thermal 58mm print format

- ✅ Customer lockdown (cashier cannot edit existing customers; new ones forced to Retail group)

### Phase 5.7 — POS Hardening + Variance Accounts

- ✅ 5-bucket COGS (8101 LPG / 8102 Cylinders / 8103 Retail / 8104 Equipment / 8105 Services)

- ✅ 5 Income accounts (7101 LPG / 7102 Cylinders / 7103 Retail / 7104 Services / 7105 Cylinders Revenue)

- ✅ expense_account + income_account set on all 143 sales items

- ✅ 4 cash variance GL accounts (2608 Cashier Recovery, 6224 Overage Suspense, 9246 Shortage Written Off, 7205 Overage Time-Barred Income)

- ✅ Backfilled 3 historical variance JEs (₦5k + ₦24k + ₦200k against Peace HR-EMP-00053)

- ✅ User ↔ Employee linkage (67/245 employees linked, all active cashiers + plant managers)

- ✅ Outlet scoping via permission_query_conditions + has_permission

- ✅ Implicit-scope fallback (POS Profile User child table)

- ✅ Owner-bypass on has_permission

- ✅ FIRS compliance: TIN, RECEIPT label, 0 % VAT explicit line on print

- ✅ Bobo Gas brand override for Itele (separate TIN, no Sungas logo, Itele address)

- ✅ Tax IDs set: Sungas 00201561-0001, Bobogas 2501110131157

### Wave A-C — Variance Enforcement

- ✅ Sungas Close Policy single doctype (thresholds, accounts, approver roles)

- ✅ Asymmetric thresholds (shortage ₦5k/₦50k, overage ₦10k/₦100k)

- ✅ Percentage rules gated by block_pct_min_expected = ₦500k

- ✅ before_submit variance enforcement (warn requires remarks, block requires approver)

- ✅ on_submit auto-post variance JE with party tagging

- ✅ variance_approved_by + variance_je walled off at permlevel 1

- ✅ Custom DocPerm: LPG Head of Operations level-0 read/write on POS Closing Shift

- ✅ Variance Approved By link filter (only approver-role users)

- ✅ Partial payments (split tender) on all 22 POS profiles

- ✅ POS Awesome Vue: unconditional variance remarks textarea + tonal severity alert

- ✅ submit_closing_shift override: draft persists on block

- ✅ Idempotent re-submission

### Phase 6 — HRMS / Nigeria Payroll (95 % DONE)

- ✅ Employee data audit (217 active staff verified)

- ✅ Master backfill (departments, designations, branches, employment types)

- ✅ 12 Salary Components (earnings + statutory + HMO + Co-op + Staff Loan)

- ✅ HMO custom fields + Sungas Standard salary structure

- ✅ 4 new payable accounts (HMO, COOP loan/contrib, Staff Loan receivable)

- ✅ 21 new payroll Cost Centers + Employee.payroll_cost_center + 217 SSAs

- ✅ Fix 10x SSA base bug (148 SSAs cancelled+resubmitted with correct Gross col)

- ✅ Residual audit + 3 missing SSAs created via fuzzy matcher

- ✅ PAYE NTAA 2025 formula live (6-bracket annualised, excludes Non-Exec/Chairman/Independent Directors)

- ✅ Operational Manuals (10 docs, 1,885 lines)

- ✅ Holiday Lists (HQ Sat+Sun, Outlets no weekly off), 233 employees assigned

- ✅ Grade Level (G1-G7) + 13th_month_eligible custom fields, 4 service providers excluded

- ✅ 6 Leave Types + 3 Policies + 229 Assignments (Annual G1=20d, G2=15d, G3-G7=10d, etc.)

- ✅ Leave Allowance (10 % basic, anniversary) + 13th Month components attached to Sungas Standard

- ✅ HR Migration Checklist + 5 templates (Bank Details, Rent Decl, Leave App, Onboarding, Exit)

- ✅ 3 Workflows: Leave + Expense (tiered) + Payroll Entry with email alerts

- ✅ NIBSS Bank Codes seeded (45 banks, Tier-1 + commercial)

- ✅ Bank Upload Generator (Stanbic + Fidelity CSVs generated for HR-PRUN-2026-00001)

- ✅ Sungas Payslip print format (clean Nigerian layout, hides India internals)

- ✅ Parallel Payroll Run preflight + slip creation (216/216 slips, 0 failed; validated to-the-kobo)

### Engagement App v1.0

- ✅ Initial scaffolding (per handoff)

### Documentation

- ✅ Operations Manual v1.1 (DOCX + Markdown shipped 2026-06)

## 3. 🔴 Phase 6 (HRMS) — Outstanding (3 items)

| # | Item | Priority | Status | Notes |
| --- | --- | --- | --- | --- |
| 6.7 | Confidentiality lockdown | 🔴 P0 | NOT STARTED | Permlevels on Salary Slip / SSA / Bank Details; 2FA enforced for HR + Finance roles; IP whitelists for sensitive doctypes |
| 6.8b | Finance sign-off on Stanbic + Fidelity bank upload CSVs | 🔴 P0 | ⏸ AWAITING FINANCE | CSVs sent 2026-05-23 |
| 6.8c | Parallel run reconciliation vs Excel | 🔴 P0 | ⏸ AWAITING USER | Re-engage once May 2026 Excel baseline uploaded to /tmp/payroll_excel_baseline.csv |

## 4. 🔴 Wave D — POS Closing Workflow + Ops Routing (NEXT)

| # | Item | Priority | Dependencies |
| --- | --- | --- | --- |
| D-1 | Sequential Workflow doctype for POS Closing Shift (Draft → Plant Mgr → HOD Ops → HOD Finance → Submitted [+ optional COO]) with severity tiers Soft/Hard/Critical | 🔴 P0 | C done |
| D-2 | Open Shift Age escalation scheduler (24h cashier+PM, 48h HOD Ops+Finance + comment, 7d MD+Audit + suspend profile) | 🔴 P0 | Brevo integration |
| D-3 | 48h SLA timer (variance approval) — auto-escalate to Path C | 🟠 P1 | D-2 |
| D-4 | Outlet Manager signature field (Path A) + COO sign-off field (Path B) | 🟠 P1 | D-1 |
| D-5 | Annex T-07 worksheet doctype (count-by-denom, cause taxonomy, photo evidence) | 🟠 P1 | — |
| D-6 | Returns / refund approval gate (Vue rebuild — manager PIN above threshold) | 🟠 P1 | Vue rebuild |
| D-7 | Inventory Purchase / Transfer / GIT routing + 48h GIT audit flag | 🟠 P1 | In-Transit warehouse setup |
| D-8 | Stock Adjustment routing (Plant+OM / HOD Ops+Finance / COO tiers) | 🟠 P1 | — |
| D-9 | Sales Register report filtered by tax_id (Rev360 export prep) | 🟡 P2 | — |

Cross-cutting infra needed: - Brevo email integration (gates D-2, D-3, D-7, Wave E-3) - Frappe Workflow JSON for severity routing (reusable across D-1, D-7, D-8)

## 5. 🟠 Wave E — Path C Fraud Protocol (4 items)

| # | Item | Priority |
| --- | --- | --- |
| E-1 | Outlet Bank Deposit Freeze flag | 🟠 P1 |
| E-2 | Cashier POS access auto-disable workflow | 🟠 P1 |
| E-3 | COO 4h notification (Brevo SMS+email) | 🟠 P1 |
| E-4 | Internal Audit case auto-open (Fraud Investigation doctype) | 🟠 P1 |

## 6. 🟠 Stakeholder SLA + KPI Reporting (cross-cutting)

| # | Item | Priority |
| --- | --- | --- |
| K-1 | Stakeholder SLA Event doctype (KPI logging for HR appraisal) | 🟠 P1 |
| K-2 | Cashier Variance Ledger report (per-cashier ageing of 2608 balances) | 🟠 P1 |
| K-3 | Stakeholder Performance L1-L5 dashboards | 🟠 P1 |
| K-4 | Month Close Health dashboard | 🟠 P1 |

## 7. 🟠 Phase A v1.1 — Engagement App Expansion

Brief received 2026-05-31 from Senior BA. Significant expansion over Sprint 0.

| # | Item | Priority |
| --- | --- | --- |
| A-1 | 21 SCL Locations doctype (region / state / PTL / CSE / FO mapping) | 🟠 P1 |
| A-2 | Customer Segmentation custom fields on Customer (segment, assigned_team, assigned_cse, assigned_location, preferred_channel, status, last_interaction_date, last_order_date, lifetime_gas_volume_kg, dnc_flag, churn_suggested_date, avg_purchase_cycle_days) | 🟠 P1 |
| A-3 | Interaction Log master doctype (customer-facing record across channels) | 🟠 P1 |
| A-4 | Support Ticket doctype (formal complaints with SLA Policy + escalation levels) | 🟠 P1 |
| A-5 | Internal SLA Task doctype (cross-team handoffs with SLA breach detection) | 🟠 P1 |
| A-6 | Weekly Engagement Plan workflow (Draft → Pending → Approved → Outcome Reported → Closed) + auto-suggest churned customers | 🟠 P1 |
| A-7 | SLA Policy doctype (auto-assignment by category+segment) | 🟠 P1 |
| A-8 | Churn Detection daily job (Retail >35d/>60d; Commercial/Bulk avg_cycle+2/+7) | 🟠 P1 |
| A-9 | Brevo WhatsApp + SMS channel for outbound + inbound | 🟢 P3 |

## 8. 🟡 Phase 5.8 / 5.9 — Continuity

| # | Item | Priority |
| --- | --- | --- |
| 5.8 | POS Backup profiles per region (Lagos1, Ogun1, Ogun2, Edo1, Delta1, Rivers1 — 6 shared profiles for Path B.2 fallback selling) | 🟡 P2 |
| 5.9 | Manual Sales Book doctype + Sales Invoice batch import (Path B.3) | 🟡 P2 |

## 9. 🟢 Phase 7 — Helpdesk

| # | Item | Priority | Notes |
| --- | --- | --- | --- |
| 7-1 | SLA Policy doctype | 🟢 P3 | Possibly merged with Engagement App A-7 |
| 7-2 | Ticket flows + assignment rules | 🟢 P3 | — |
| 7-3 | Email integration | 🟢 P3 | Already have helpdesk app installed |
| 7-4 | Customer-facing portal | 🟢 P3 | — |

## 10. 🟢 Phase 8 — CRM

| # | Item | Priority |
| --- | --- | --- |
| 8-1 | Lead/Opportunity pipeline | 🟢 P3 |
| 8-2 | Weekly engagement dashboard | 🟢 P3 |
| 8-3 | CRM ↔ Engagement App data sync | 🟢 P3 |

## 11. 🟢 Phase 9 — Period Close + Cutover

| # | Item | Priority |
| --- | --- | --- |
| 9-1 | Month Close Pack workflow doctype (Draft → HOD Finance → Head Internal Control → COO → Locked) | 🟢 P3 |
| 9-2 | Opening Balances import | 🟢 P3 |
| 9-3 | UAT + cutover | 🟢 P3 |

## 12. 🟢 Phase 10 — Budgeting

| # | Item | Priority |
| --- | --- | --- |
| 10-1 | ERPNext Budget doctype against Cost Centers | 🟢 P3 |
| 10-2 | Annual Compensation Cost dashboard (month-by-month forecast incl. 13th Month spike + Leave Allowance bumps) | 🟢 P3 |

## 13. 🟢 Engineering / Manufacturing Backlog

| # | Item | Priority |
| --- | --- | --- |
| ENG-1 | Equipment & Services inventory onboarding (engineering equipment avg ₦6M — reticulation/combustion/conversion/fabrication/corrosion-control under Item Group Equipment; service items under Services) | 🟢 P3 |
| ENG-2 | Services Quotation + Project Costing workflow (Project + BOM + Sales Order with sub-assemblies) | 🟢 P3 |
| ENG-3 | Manufacturing data hygiene — flip is_sales_item=0 on Raw Material + Sub Assemblies items (143 sales items today) | 🟢 P3 |

## 14. 🟡 Bank Statement App (Existing, Needs UAT)

23 doctypes already built in /app/forks/Bank-Statement (bank_account_limit, bank_statement, bank_statement_format, bank_statement_item, bank_statement_mapping_item, bank_transaction_type, document_party_type, document_type_to_be_paid, merged_payment_beneficiaries, payment_advice, payment_advice_item, payment_instruction, payment_proposal_item, payment_run, payment_run_filter, payment_run_filter_item, payment_run_settings, third_party_search_fields, transaction_type_journal_template, voucher_search_key, voucher_search_specifications, …).

| # | Item | Priority |
| --- | --- | --- |
| B-1 | Deploy Bank-Statement app to Frappe Cloud bench | 🟡 P2 |
| B-2 | Wire bank statement formats per Sungas bank (Stanbic, Fidelity, GTB, etc.) | 🟡 P2 |
| B-3 | Payment Run UAT with finance team | 🟡 P2 |
| B-4 | Decide: integrate this app’s Payment Advice with HR bank upload (6b)? | 🟡 P2 |

## 15. 🟡 Compliance / Reporting Backlog

| # | Item | Priority |
| --- | --- | --- |
| R-1 | NRS Rev360 monthly VAT Schedule export (bench command, ~45 min build) | 🟡 P2 |
| R-2 | ERPNext Sales Register quick-win for VAT (configure filtered view by tax_id, monthly close pack input) | 🟡 P2 |

## 16. 📦 Other / Misc Backlog

| # | Item | Priority |
| --- | --- | --- |
| B-5 | Head of Finance (non-LPG) duplicate role cleanup — merge 1 user into LPG Head of Finance | 🟡 P2 |
| B-6 | Vue rebuild for “Draft Saved” follow-up banner in ClosingDialog (currently uses Frappe msgprint) | 🟢 P3 |
| B-7 | Customer Facing Screen (dual-display POS Awesome) | 🟢 P3 |
| B-8 | UpdateCustomer.vue z-index nit (toast hidden behind modal) | 🟢 P3 |
| B-9 | Test bench / staging site provisioning | 🟡 P2 |
| B-10 | PAT rotation policy (7-day rotation, “Save to GitHub” guidance) | 🟡 P2 |

## 17. Suggested Build Order (next 6-8 weeks)

Week 1  ─── Phase 6.8b/6.8c HRMS close-out (P0 — payroll cutover sign-off)
        └── Brevo integration playbook + sandbox account

Week 2  ─── Wave D-1 (Sequential Workflow doctype) build + UAT
        └── Phase 6.7 (Confidentiality lockdown)

Week 3  ─── Wave D-2 (Open Shift Age scheduler) build + UAT
        └── Wave D-3 (48h SLA timer)

Week 4  ─── Wave D-4 (Outlet Mgr / COO signatures)
        └── Wave D-5 (Annex T-07 worksheet)

Week 5  ─── Wave D-6 (Returns approval — Vue rebuild)
        └── Wave D-7 (Purchase / Transfer / GIT routing) — In-Transit warehouse setup

Week 6  ─── Wave D-8 (Stock Adjustment routing) + Wave D-9 (Sales Register / Rev360)
        └── K-1, K-2 (Stakeholder SLA Event doctype + Cashier Variance Ledger report)

Week 7  ─── Wave E (Path C fraud protocol: E-1..E-4)
        └── K-3, K-4 (Stakeholder Performance + Month Close Health dashboards)

Week 8  ─── Phase A v1.1 (Engagement App expansion: A-1 Locations + A-2 Segmentation + A-3 Interaction Log)
        └── Phase 5.8 (Backup profiles) + 5.9 (Manual Sales Book)

Stretch ─ Phase A v1.1 continued (A-4..A-8: Tickets, Internal SLA, Engagement Plan, SLA Policy, Churn)
        ├── Bank Statement app UAT + deploy
        ├── R-1 (Rev360 export) + R-2 (Sales Register)
        ├── Phase 9 (Month Close Pack)
        ├── Phase 10 (Budgeting)
        └── Engineering / Manufacturing onboarding

## 18. Open Questions for User Decision

Before Wave D-1 build starts:

- Severity tiers for D-1 — define Soft / Hard / Critical band cutoffs. Today: Warn ₦5k, Block ₦50k. Need a third “Critical” tier (e.g. ₦200k+ ? or 5 %+ ?) to trigger HOD Finance + COO routing.

- Outlet Manager mapping — for D-2 (24h email). Custom field on POS Profile, or Employee doctype with designation filter?

- Brevo account — does Sungas already have one? Otherwise we need to provision + get API key.

- Phase 6 close-out — May 2026 Excel reconciliation baseline upload + Finance bank-CSV sign-off. Are these still on track?

- Staging bench — provision a clone of sungasmis.v.frappe.cloud for Wave D testing, or continue direct-to-prod?

- Engagement App v1.1 ordering — A-1 (21 Locations) is foundational and the rest depend on it. Build now or wait until after Wave D?

- Bank Statement app — fully spec’d out, just needs UAT. Schedule UAT week for finance team?

## 19. What I missed in the v1 roadmap (full disclosure)

For transparency — these were dropped from the prior consolidation and are now restored:

- Phase 6 (HRMS) — listed as “active” with 5 items, but PRD shows it’s 95 % done with only 3 outstanding (6.7 confidentiality, 6.8b finance sign-off, 6.8c reconciliation). My prior table over-stated remaining work.

- Phase 7 (Helpdesk), Phase 8 (CRM) — entire phases missing from v1.

- Phase A v1.1 — listed only 3 items; the actual spec has 9.

- Stakeholder SLA + KPI layer — entire cross-cutting area missing from v1.

- Phase 10 (Budgeting) — missing.

- Engineering / Manufacturing backlog (Equipment onboarding, Services quotation, manufacturing hygiene) — missing.

- Bank Statement app — already-built 23 doctypes that need UAT, missing from v1.

- Variance lifecycle accounts — full chain (2608 → 9246 written off, 6224 → 7205 time-barred income) was not described.

- Compliance / Reporting backlog (Rev360 export, Sales Register VAT) — missing.

This v2 roadmap is the canonical version. Treat the prior v1 (ROADMAP.md commit ff003aa) as superseded.

End of Roadmap v2. Re-issued at each Wave completion. Will be re-circulated post Wave D-2 with timing actuals.